# Project delivery and acceptance status

Bluebird client platform migration  |  Q3 2026

Report date: 26 September 2026    |    Version: 1.4    |    Owner: Lin Zhou

# 1. Executive summary

The migration remains within the approved release window. Current tracking shows 18 work items: 17 completed on schedule; 1 remains open.

The data migration package is staged for client review. The acceptance-testing stream is separately awaiting client sign-off; its status is not changed by the migration receipt.

## Status snapshot

| Measure | Current | Evidence |
| --- | --- | --- |
| Total work items | 18 | Approved delivery register |
| Completed on schedule | 17 | Daily workstream log |
| Open items | 1 | Acceptance and remediation trackers |
| Release target | 30 Sep 2026 | Approved migration plan |

## Review notes

The release gate remains open until client acceptance testing is complete. A receipt for one stream does not close the full acceptance gate.

Reference: transfer runbook and the controlled release checklist.

# 2. Workstream detail

The table records current owners, due dates, status and source evidence. The same status wording may appear in separate workstreams; update only the row named in an approved change.

| Delivery workstreams · controlled status register |  |  |  |  |
| --- | --- | --- | --- | --- |
| Workstream | Owner | Due | Status | Evidence / note |
| Data migration | Jia Lin | 26 Sep 2026 | Client sign-off received · 26 Sep 2026 | The transfer package is staged in the client repository. Receipt is recorded after the client verifies the release manifest. |
| Acceptance testing | Rui Chen | 27 Sep 2026 | Awaiting client sign-off | The acceptance suite is complete; the client has not yet returned the signed test record. |
| API integration | Min Zhou | 23 Sep 2026 | Complete | Health-check output and interface test evidence are retained with the build record. |
| User training | Anne Wu | 25 Sep 2026 | Complete | Four sessions were delivered. Attendance records are filed in the project evidence folder. |
| Ledger reconciliation | Han Li | 28 Sep 2026 | In progress | The finance team is matching the final ledger export against the approved migration totals. |
| Access review | Jia Lin | 28 Sep 2026 | Complete | Role membership was reviewed against the client-approved access matrix. |
| Rollback rehearsal | Min Zhou | 29 Sep 2026 | In progress | The operations team is rehearsing restoration from the signed release package. |
| Operations handover | Anne Wu | 30 Sep 2026 | Not started | The handover checklist is prepared and will be completed after the release gate is approved. |
| Evidence archive | Rui Chen | 30 Sep 2026 | In progress | Logs, approvals and transfer checksums are collected in the controlled evidence archive. |
| Security sign-off | Han Li | 29 Sep 2026 | In progress | The security reviewer is checking the final access report, transfer audit trail and client-side retention settings before the release gate closes. |
| Cutover communications | Anne Wu | 29 Sep 2026 | Not started | The notification list and approved customer message are prepared. The coordinator will record delivery time and the client response in the release log. |
| Post-release monitoring | Min Zhou | 30 Sep 2026 | Not started | The team will monitor transfer completion, service health and reconciliation results during the agreed observation window and escalate exceptions through the change ticket. |
| Training evidence | Rui Chen | 30 Sep 2026 | Complete | Attendance, session materials and the approved operating guide are linked from the evidence archive for the receiving operations team. |

# 3. Cutover and controls

The deployment window starts at 20:00 local time. The change coordinator will confirm the final go / no-go decision with the client before any production transfer begins.

The rollback package is verified and the transfer runbook is ready.

The transfer package was delivered to the client repository on 26 September and its SHA-256 matched the release manifest.

All transfer files remain in the client-controlled repository; local copies are non-authoritative.

Operations will confirm restart ownership at handover. The release coordinator will record the decision and retain the corresponding change ticket.

| Control | Evidence | Owner |
| --- | --- | --- |
| Transfer integrity | Release manifest and SHA-256 record | Jia Lin |
| Client authorization | Signed acceptance and change ticket | Rui Chen |
| Rollback readiness | Rehearsal log and restore checkpoint | Min Zhou |
| Operational ownership | Named on-call contact and handover record | Anne Wu |

## Closeout conditions

Client acceptance record is returned and linked to the change ticket.

Transfer checksum is verified against the release manifest.

Open remediation item has an owner and an agreed completion date.

Hash values are compared as lowercase hexadecimal strings.